## Team Members
Enter the First Name of Each Team Member | HOW TO USE: | 1. File Menu --> Make a copy
Suliman Alhamidi |  | 2. Save to one team member's Google drive
Abdullah Abdulaziz Almutairi |  | 3. Share file with other team members
Ali Saleh Al-Suhibani |  | 4. Edit First Names on this tab
Mohammed Zaid Almogherah |  | 5. Add your team name to the name of this document
Abdullah Hamad Al Askar |  | 6. For each sprint, duplicate the sprint template and change the start date
DOCUMENT HISTORY
| 2017-09-20 | Created by Justin Sybrandt (http://sybrandt.com/post/google-slides-agile/)
| 2019-03-23 | Modified by Susanne Sherba for use in COMP 3381 (Software Engineering I)

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
S1 | 1 | Sign Up | As a new user, I want to be able to register |  | High | Done
S1 | 2 | Start Game | As a user, I want the ability to initiate a new game on the game |  | High | Done
S1 | 3 | Display Stages | As a user, I want to see all game stages |  | High | Done
S1 | 4 | Display Level | As a user, I want to easily view information about the current level I am at in the game |  | Medium | Done
S1 | 5 | Back Forward | As a user, I desire the capability to navigate seamlessly within the game environment |  | Medium | Done
S2 | 6 | Calculate Player Level | As a user, I expect the system to calculate and display my overall player level or score |  | Medium | Done
S2 | 7 | Access Stages | As a user, I want the system to verify whether I am authorized to access a specific stage when I attempt to click on it |  | High | Done
S2 | 8 | Generate Words | As a game developer, I want to implement a feature that generates unique and engaging words for each level in the game |  | High | Done
S2 | 9 | Insert Letter | As a user, I want the ability to insert letters into a word during gameplay |  | High | Done
S2 | 10 | Remove Letter | As a user, I would like the option to remove a letter from a word during gameplay |  | Medium | Done
S2 | 11 | Hint Player | As a user, I expect the game to offer hints |  | Medium | Done
S2 | 12 | Check Answer | As a developer, I want to implement a function that checks whether the player's input corresponds to the correct answer in the game |  | High | Done
S2 | 13 | Change Word | As a user, I want the ability to change the difficulty level of a word in the game |  | Medium | Done
S2 | 14 | End of Stage | As a game developer, I want to implement a mechanism to handle the conclusion of each game stage |  | High | Done
S3 | 15 | Popup Screen | As a user, I want the game to display popups for important information |  | Low | Done
S3 | 16 | Menu Bar | As a user, I expect the game to include a menu bar with various options |  | Medium | Done
S3 | 17 | Turn On Sound | As a user, I want the option to enable game sounds |  | Low | Done
S3 | 18 | Turn Off Sound | As a user, I want the option to disable game sounds |  | Low | Done
S3 | 19 | Display Trip Progress | As a user, I expect the game to visually represent and display the progress of my journey within the gaming environment |  | Medium | Done
S3 | 20 | The End of the Game | As a game developer, I want to implement a comprehensive mechanism to handle the conclusion of the game |  | Medium | Done
S3 | 21 | Congrats Score | As a game developer, I want to implement a feature that displays the player's score and a congratulations message upon the successful conclusion of the game |  | Medium | Done
S3 | 22 | Download Trip Info | As a user, I want the ability to download comprehensive information about my entire gaming journey for reference or sharing purposes |  | Low | Done
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 1-high | To Do
[5 empty] | 2-medium | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do

## Sprint 1
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
1 | Create Sign-Up Screen | 2 | 2 | Suliman Alhamidi | Done | 2024-08-01 | Sprint Number: | 1 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2024-03-01 | 2024-09-01 | 45536 |  | 7
2 | Create Start Button in the main page to allow game starting | 2 | 1 | Abdullah Abdulaziz Almutairi | Done | 2024-09-01 | Start Date: | 2024-03-01 | Suliman Alhamidi | 2 | 2 | 100% | #NAME? | 0 | 45536 | #NAME? | 5.8333
3 | Create a widget containing all game stages | 1 | 1 | Ali Saleh Al-Suhibani | Done | 2024-09-01 | Sprint Length | 6 | Abdullah Abdulaziz Almutairi | 2 | 2 | 100% | #NAME? | 0 | 45536 | #NAME? | 4.6667
4 | Create small screen to display user level | 1 | 1 | Mohammed Zaid Almogherah | Done | 2024-09-01 | Hours Per Day: | 1.1667 | Ali Saleh Al-Suhibani | 1 | 1 | 100% | #NAME? | 0 | 45536 | #NAME? | 3.5
5 | Create back button | 1 | 1 | Abdullah Hamad Al Askar | Done | 2024-09-01 |  |  | Mohammed Zaid Almogherah | 1 | 1 | 100% | #NAME? | 0 | 45536 | #NAME? | 2.3333
[5 empty] | To Do |  |  |  | Abdullah Hamad Al Askar | 1 | 1 | 100% | #NAME? | 0 | 45536 | #NAME? | 1.1667
[5 empty] | To Do |  |  |  | 0 | 0 | 0 | 0% | #NAME? | 0 | 45536 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 45536 | #NAME? | 0
[5 empty] | To Do |  |  |  | Total: | 7 | 7 | 100% | #NAME? | 0 | 45536 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 45536 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 45536 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 45536 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 45536 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 45536 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 45536 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 2
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
6 | Calculate the overall user level before displaying it on the screen, based on the user's score | 2 | 2 | Abdullah Hamad Al Askar | Done | 14/1/2024 | Sprint Number: | 2 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2024-10-01 | 20/1/2024 | 20/1/2024 |  | 22
7 | Check if the user authorized to be access the clicked stage | 3 | 2 | Ali Saleh Al-Suhibani | Done | 14/1/2024 | Start Date: | 2024-10-01 | Suliman Alhamidi | 4 | 4 | 100% | #NAME? | 0 | 0 | #NAME? | 21
8 | Generate words for each level | 4 | 3 | Suliman Alhamidi | Done | 15/1/2024 | Sprint Length | 22 | Abdullah Abdulaziz Almutairi | 5 | 5 | 100% | #NAME? | 0 | 0 | #NAME? | 20
9 | Allow users to insert letters into the word | 2 | 1 | Ali Saleh Al-Suhibani | Done | 16/1/2024 | Hours Per Day: | 1 | Ali Saleh Al-Suhibani | 5 | 5 | 100% | #NAME? | 0 | 0 | #NAME? | 19
10 | Implement the ability to remove letters from the word | 2 | 2 | Abdullah Hamad Al Askar | Done | 16/1/2024 |  |  | Mohammed Zaid Almogherah | 4 | 4 | 100% | #NAME? | 0 | 0 | #NAME? | 18
11 | Provide hints to help the player | 3 | 2 | Mohammed Zaid Almogherah | Done | 16/1/2024 |  |  | Abdullah Hamad Al Askar | 4 | 4 | 100% | #NAME? | 0 | 0 | #NAME? | 17
12 | Implement a function to check the correct answer | 1 | 1 | Mohammed Zaid Almogherah | Done | 18/1/2024 |  |  | 0 | 0 | 0 | 0% | #NAME? | 0 | 0 | #NAME? | 16
13 | Allow users to change the difficult word | 3 | 3 | Abdullah Abdulaziz Almutairi | Done | 18/1/2024 | [6 empty] | #NAME? | 0 | 0 | #NAME? | 15
14 | Handle the conclusion of each game stage | 2 | 2 | Abdullah Abdulaziz Almutairi | Done | 20/1/2024 |  |  | Total: | 22 | 22 | 100% | #NAME? | 0 | 0 | #NAME? | 14
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 13
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 12
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 11
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 10
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 9
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 8
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 7
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 6
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 5
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 4
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 3
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 2
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 1
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 3
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
15 | Display popups for important information | 3 | 2 | Mohammed Zaid Almogherah | Done | 25/1/2024 | Sprint Number: | 3 | Person | Hours Assigned | Hours Completed | Percentage Complete | 17/1/2024 | 0 | 0 |  | 14
16 | Include a menu bar with various options | 2 | 2 | Ali Saleh Al-Suhibani | Done | 25/1/2024 | Start Date: | 17/1/2024 | Suliman Alhamidi | 2 | 2 | 100% | #NAME? | 0 | 0 | #NAME? | 13
17 | Allow users to enable game sounds | 1 | 2 | Abdullah Hamad Al Askar | Done |  | Sprint Length | 14 | Abdullah Abdulaziz Almutairi | 3 | 3 | 100% | #NAME? | 0 | 0 | #NAME? | 12
18 | Provide an option to disable game sounds | 1 | 1 | Abdullah Hamad Al Askar | Done |  | Hours Per Day: | 1 | Ali Saleh Al-Suhibani | 3 | 3 | 100% | #NAME? | 0 | 0 | #NAME? | 11
19 | Show the progress of the user's journey | 2 | 1 | Suliman Alhamidi | Done |  |  |  | Mohammed Zaid Almogherah | 3 | 3 | 100% | #NAME? | 0 | 0 | #NAME? | 10
20 | Handle the conclusion of the game | 3 | 2 | Abdullah Abdulaziz Almutairi | Done |  |  |  | Abdullah Hamad Al Askar | 3 | 3 | 100% | #NAME? | 0 | 0 | #NAME? | 9
21 | Display the player's score and congratulations message | 1 | 3 | Abdullah Hamad Al Askar | Done |  |  |  | 0 | 0 | 0 | 0% | #NAME? | 0 | 0 | #NAME? | 8
22 | Allow users to download whole journey information | 1 | 1 | Ali Saleh Al-Suhibani | Done | [7 empty] | #NAME? | 0 | 0 | #NAME? | 7
[5 empty] | To Do |  |  |  | Total: | 14 | 14 | 100% | #NAME? | 0 | 0 | #NAME? | 6
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 5
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 4
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 3
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 2
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 1
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")